## ProjectTaskList
PROJECT TASK LIST |  |  |  | ENGLISH VOCABULARY
Project Start | 2018-12-11 |  |  |  |  | Project End | 2018-12-24
TASK | OWNER | PRIORITY | START | END | % COMPLETE | DONE | NOTES
Requirements | [5 empty] | 0
Introduction | Lê Nguyên Hoài Nghĩa | HIGH | 2018-12-11 | 2018-12-12 | 100% | 1 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Hight Level Requirements | Nguyễn Văn Hải | HIGH | 2018-12-12 | 2018-12-14 | 100% | 1 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Functional Requirements | Nguyễn Tiến Dũng | MEDIUM | 2018-12-14 | 2018-12-16 | 100% | 1 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Non-functional Requirements | Nguyễn Trần Quốc Vương | MEDIUM | 2018-12-14 | 2018-12-16 | 100% | 1 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Other requirements and main screen design | Võ Minh Hiếu | LOW | 2018-12-16 | 2018-12-18 | 100% | 1 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Design | [5 empty] | 0
login and registration | Nguyễn Tiến Dũng | LOW | 2018-12-16 | 2018-12-18 | 100% | 1 | The interface exactly matches the requirements set. Some parts need correcting
Main screen | Lê Nguyên Hoài Nghĩa | HIGH | 2018-12-16 | 2018-12-18 | 100% | 1 | The interface exactly matches the requirements set. Some parts need correcting
Detail screen | Nguyễn Văn Hải | HIGH | 2018-12-16 | 2018-12-18 | 100% | 1 | The interface exactly matches the requirements set. Some parts need correcting
| Võ Minh Hiếu | HIGH | 2018-12-16 | 2018-12-19 | 100% | 1 | The interface exactly matches the requirements set. Some parts need correcting
| Nguyễn Trần Quốc Vương | HIGH | 2018-12-16 | 2018-12-19 | 100% | 1 | The interface exactly matches the requirements set. Some parts need correcting
Code - Front end | [5 empty] | 0
Registration | Nguyễn Tiến Dũng | MEDIUM | 2018-12-18 | 2018-12-20 | 90% | 0 | Code clean, easy to understand but there are some missing functions.
Home screen | Lê Nguyên Hoài Nghĩa | HIGH | 2018-12-18 | 2018-12-20 | 90% | 0 | Code clean, easy to understand but there are some missing functions.
Detail screen | Nguyễn Văn Hải | HIGH | 2018-12-19 | 2018-12-21 | 80% | 0 | Code clean, easy to understand but there are some missing functions.
| Nguyễn Trần Quốc Vương | HIGH | 2018-12-19 | 2018-12-21 | 80% | 0 | Code clean, easy to understand but there are some missing functions.
| Võ Minh Hiếu | HIGH | 2018-12-19 | 2018-12-21 | 80% | 0 | Code clean, easy to understand but there are some missing functions.
Code - Back end | [5 empty] | 0
Registration | Nguyễn Văn Hải | LOW | 2018-12-21 | 2018-12-22 | 80% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Search words | Nguyễn Trần Quốc Vương | MEDIUM | 2018-12-20 | 2018-12-23 | 80% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
| Võ Minh Hiếu | MEDIUM | 2018-12-20 | 2018-12-23 | 80% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Learning vocabulary | Nguyễn Tiến Dũng | HIGH | 2018-12-20 | 2018-12-23 | 80% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
| Lê Nguyên Hoài Nghĩa | HIGH | 2018-12-20 | 2018-12-23 | 80% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Unit Testing | [5 empty] | 0
Re-check customer requirements | All team | HIGH | 2018-12-24 | 2018-12-24 | 100% | 1 | Has reached the customer's requirements
Check requirements | All team | MEDIUM | 2018-12-24 | 2018-12-24 | 100% | 1 | Has reached the customer's requirements
Check front end | All team | MEDIUM | 2018-12-24 | 2018-12-24 | 90% | 0 | Tested the product but there are some minor bugs in the improvement process
Check back end | All team | MEDIUM | 2018-12-24 | 2018-12-24 | 90% | 0 | Tested the product but there are some minor bugs in the improvement process